## Risk Register
Risk ID | Risk Description | Impact | Likelihood | Inherent Risk | Existing Controls | Residual Risk | Risk Owner | Framework Reference | CSF Informative Reference | Status
R-001 | Unpatched operating systems may allow unauthorized access or malware infection | High | Medium | High | Automated patch management via WSUS and AWS Systems Manager; Monthly vulnerability scans (Nessus) | Medium | IT Operations | NIST CSF PR.IP-12 / SOC 2 CC7.1 | NIST SP 800-53: SI-2, CM-2 / ISO 27001: A.12.6.1 | Mitigated
R-002 | Misconfigured S3 bucket may lead to exposure of sensitive data | High | Medium | High | S3 bucket policies audited quarterly; AWS Config rules for public access | Low | Cloud Security | NIST CSF PR.AC-5 / SOC 2 CC6.6 | NIST SP 800-53: AC-3, AC-6 / ISO 27001: A.9.2.3 | Mitigated
R-003 | Excessive user privileges increase risk of unauthorized changes | High | High | High | Quarterly access reviews; RBAC enforced in Active Directory and Azure AD | Medium | Security Operations | NIST CSF PR.AC-1 / SOC 2 CC6.2 | NIST SP 800-53: AC-2 / ISO 27001: A.9.2.2 | Open
R-004 | Lack of offsite backups could lead to data loss in disaster scenarios | High | Low | Medium | Automated daily backups to encrypted AWS S3; tested quarterly | Low | Infrastructure | NIST CSF PR.IP-4 / SOC 2 CC7.2 | NIST SP 800-53: CP-9 / ISO 27001: A.12.3.1 | Mitigated
R-005 | No formal incident response plan may delay recovery and reporting | High | Medium | High | Draft IR plan in progress; simulated tabletop exercises planned | Medium | Compliance | NIST CSF RS.RP-1 / SOC 2 CC7.4 | NIST SP 800-53: IR-1 / ISO 27001: A.16.1.1 | In Progress
R-006 | Third-party vendor may not meet security expectations | Medium | Medium | Medium | Vendor security questionnaires (SIG Lite) and SOC 2 reviews annually | Low | Procurement | NIST CSF ID.SC-4 / SOC 2 CC3.1 | NIST SP 800-53: SA-9 / ISO 27001: A.15.1.1 | Mitigated
R-007 | Unencrypted endpoint devices could leak sensitive data | High | Low | Medium | Full disk encryption via BitLocker; endpoint monitoring via Defender for Endpoint | Low | IT Security | NIST CSF PR.DS-1 / SOC 2 CC6.7 | NIST SP 800-53: SC-28 / ISO 27001: A.10.1 | Mitigated
R-008 | Weak password policy increases likelihood of credential theft | High | Medium | High | Enforced 15-character minimum and MFA; password rotation every 90 days | Low | IT Security | NIST CSF PR.AC-1 / SOC 2 CC6.1 | NIST SP 800-53: IA-5 / ISO 27001: A.9.4.3 | Mitigated

## Overview
Project Overview
This sample IT Risk Register was developed as part of a Governance, Risk, and Compliance (GRC) lab.
It identifies, evaluates, and tracks common IT and cloud infrastructure risks mapped to NIST CSF and SOC 2.
Risk Scoring Methodology:
- Impact: Low / Medium / High based on potential business disruption or data loss.
- Likelihood: Low / Medium / High based on probability of occurrence.
- Inherent Risk: Calculated from Impact × Likelihood before controls.
- Residual Risk: Remaining risk after existing controls are implemented.
CSF Informative References:
NIST CSF controls are mapped to underlying standards such as NIST SP 800-53 and ISO/IEC 27001.
Example:
- PR.IP-12 → NIST SP 800-53 SI-2 (Flaw Remediation)
- PR.AC-1 → ISO/IEC 27001 A.9.2.2 (User Access Management)